Travis Harvey

Tennessee Tech Box 10908

Cookeville, TN 38505

April 14, 2004

Tennessee Tech University

Cookeville, TN 38505

Re: Progress Report on Barred Owl population in Bowater Pocket Wilderness.

To Whom It May Concern:

I am happy to discuss with you the progress of my report. The population of a bird of prey in an area is a wealth of knowledge about the area in which, everyone will benefit. In doing this report I hope to give knowledge to the fact of what is there.

The attached progress report contain what I have accomplished up to date, including my timeline and description of what I have done up to now.

I am certain that you will find that I have met or exceeded what I have planned to do until now.

Sincerely,

Travis Harvey

Barred Owl Population in the Bowater Pocket Wilderness Progress Report

Travis Harvey

Tennessee Tech University

April 14, 2004

Table of Contents

- Letter of Transmittal

- Cover Page

- Body of Progress Report

- Appendices

Progress Report

The work I have accomplished up to date includes completing my research, gathering materials needed to finish research and gathering resources needed to begin my manuscript.

Plans anticipated for finishing my project include finishing my manuscript, gathering material for the poster and having my manuscript checked and approved by 3 separate sources.

The only problem that I have encountered while doing the report is getting the test animals to respond to my calls and the location of the project area. There were also some other problems with financing but nothing that could not be handled.

Appendices

PERT Chart

Project Timeline:

January:   Create idea for project

February: Create hypothesis

Gather research for basis of project

Start research proposal

Create Data Form

March:    Create power point presentation for research proposal

Give proposal to group

Start on research

Create tables and data based on research

April:      Finish research

Put together data

Begin manuscript with data collected

Finish manuscript

May:   Present finished research