## Slide 1: Project Management in Practice
Prepared by
Scott M. Shafer
Wake Forest University
Mantel, Meredith, Shafer, and Sutton
John Wiley and Sons, Inc.

## Slide 2: Chapter 3
Planning the Project

## Slide 3: Two Extremes
“Ready, Fire, Aim”
“Paralysis by Analysis”

## Slide 4: THE CONTENTS OF A PROJECT PLAN

## Slide 5: Elements of Project Master Plan
Overview
  brief description of project
  deliverables
  milestones
  expected profitability and competitive impact
  intended for senior management
Objectives
  detailed description of project’s deliverables
  project mission statement

## Slide 6: Elements of Project Master Plan continued
General Approach
  technical and managerial approaches
  relationship to other projects
  deviations from standard practices
Contractual Aspects
  agreements with clients and third parties
  reporting requirements
  technical specifications
  project review dates

## Slide 7: Elements of Project Master Plan continued
Schedules
  outline of all schedules and milestones
Resource Requirements
  estimated project expenses
  overhead and fixed charges
Personnel
  special skill requirements
  necessary training
  legal requirements

## Slide 8: Elements of Project Master Plan concluded
Evaluation Methods
  evaluation procedures and standards
  procedures for monitoring, collecting, and storing data on project performance
Potential Problems
  list of likely potential problems

## Slide 9: THE PLANNING PROCESS

## Slide 10: PM’s First Job
Understand the expectations that the organization has for the project.
Identify who among senior managers has a major interest in the project.
Determine if anything about the project is atypical.

## Slide 11: Developing Invitation List
At least one representative from senior management.
Managers from functional areas that will contribute to the project.
Perhaps highly specialized technical experts.

## Slide 12: The Launch Meeting
Senior Management Introduces PM
PM Chairs Meeting
  develop general understanding of the functional inputs the project will need
  may brainstorm the problem
  may develop preliminary plan
Important Results
  scope understood and temporarily fixed
  functional managers understand their responsibilities and have committed to developing the initial plan

## Slide 13: Sorting Out the Project
Hierarchical Planning Process
  begin with project’s objectives
  list major activities needed to achieve objectives (Level 1 Activities)
  delegate level 1 activities to individuals or functional areas to develop list of Level 2 activities …
  degree of detail should be same within a given level

## Slide 14: Figure 3-1 Three Levels of Detail in Hierarchical Planning

## Slide 15: Creating the Project Action Plan
Project activities identified and arranged in successively finer detail (by levels).
Type and quantity of each required resource identified for each activity.
Predecessors and durations estimated for each activity.
Milestones identified.
Individual or group assigned to perform the work identified for all activities.

## Slide 16: Using the Project Action Plan
Project Master Schedule created by combining milestones, durations, and predecessors
  used to compare actual and planned performance
Use of Templates

## Slide 17: THE WORK BREAKDOWN STRUCTURE

## Slide 18: Simple Approach for Creating the WBS
Gather Project Team
Provide Team Members with Pad of Sticky-Notes
Team Members Write Down all Tasks They can Think of.
Sticky-Notes Placed and Arranged on Wall

## Slide 19: Figure 3-4 A Partial WBS (Gozinto Chart) for an Annual Tribute Dinner Project

## Slide 20: Figure 3-5 A Linear Responsibility Chart

## Slide 21: MULTIDISCIPLINARY TEAMS -- BALANCING PLEASURE AND PAIN

## Slide 22: Concurrent Engineering
Carrying out steps concurrently rather than sequentially
  also referred to as simultaneous engineering
Key Advantages
  helps minimize conflict across functional groups
  reduces project duration

## Slide 23: Interface Coordination -- Interface Management
Key challenge facing PM is coordinating work of different functional groups.
One approach is to identify and map the interdependencies between members of the project team.

## Slide 24: Figure 3-6 An Interface Mapping of a Silicon Chip Design Project

## Slide 25: Figure 3-7 A Coordination Structure Model for Project Management

## Slide 26: Comments on Empowerment and Work Teams
Participatory Management
Success of empowered teams depends heavily on how team program implemented

## Slide 27: Advantages of Empowerment
High quality solutions
Avoid micromanagement
Team has accountability for part of project deliverable
Synergistic solutions
Tool for timely evaluation and feedback

## Slide 28: Copyright
Copyright John Wiley & Sons, Inc. All rights reserved. Reproduction or translation of this work beyond that named in Section 117 of the United States Copyright Act without the express written consent of the copyright owner is unlawful. Requests for further information should be addressed to the Permissions Department, John Wiley & Sons, Inc. Adopters of the textbook are granted permission to make back-up copies for their own use only, to make copies for distribution to students of the course the textbook is used in, and to modify this material to best suit their instructional needs. Under no circumstances can copies be made for resale. The Publisher assumes no responsibility for errors, omissions, or damages, caused by the use of these programs or from the use of the information contained herein.