## Slide 1: Project Management in Practice
Prepared by
Scott M. Shafer
Wake Forest University
Mantel, Meredith, Shafer, and Sutton
John Wiley and Sons, Inc.

## Slide 2: Chapter 5
Scheduling the Project

## Slide 3: PERT AND CPM NETWORKS

## Slide 4: History
Late 1950s
  Program Evaluation and Review Technique (PERT)
    U.S. Navy, Booz-Allen Hamilton, and Lockeheed Aircraft
    Probabilistic activity durations
  Critical Path Method (CPM)
    Dupont De Nemours Inc.
    Deterministic activity durations

## Slide 5: The Language of PERT/CPM
Activity
  task or set of tasks
  use resources
Event
  state resulting from completion of one or more activities
  consume no resources or time
  predecessor activities must be completed

## Slide 6: The Language of PERT/CPM continued
Milestones
  events that mark significant progress
Network
  diagram of nodes and arcs
  used to illustrate technological relationships
Path
  series of connected activities between two events

## Slide 7: The Language of PERT/CPM concluded
Critical Path
  set of activities on a path that if delayed will delay completion of project
Critical Time
  time required to complete all activities on the critical path

## Slide 8: Building the Network
AOA Network
AON Network

## Slide 9: Table 5-1 A Sample Set of Project Activities and Precedences

## Slide 10: Figure 5-1 Stage 1 of a Sample AON Network

## Slide 11: Figure 5-2 Stage 2 of a Sample AON Network

## Slide 12: Figure 5-3 A Completed Sample AON Network

## Slide 13: Figure 5-4 Stage 1 of a Sample AOA Network

## Slide 14: Figure 5-5 Stage 2 of a Sample AOA Network

## Slide 15: Figure 5-6a A Completed Sample AOA Network

## Slide 16: Figure 5-6b A Completed Sample AOA Network Showing the Use of a Dummy Task

## Slide 17: Table 5-2 A Sample Problem for Finding the Critical Path and Critical Time

## Slide 18: Figure 5-7 Stage 1 of a Sample Network

## Slide 19: Figure 5-8 A Complete Network

## Slide 20: Figure 5-9 Information Contents in an AON Node

## Slide 21: Figure 5-10 The Critical Path and Time for Sample Project

## Slide 22: Calculating Activity Slack
Slack or Float
  LST - EST = LFT - EFT = Slack

## Slide 23: Figure 5-11 An MSP Version of PERT/CPM Network

## Slide 24: Figure 5-12 A Modified Version of MSP Network

## Slide 25: PROJECT UNCERTAINTY AND RISK MANAGEMENT

## Slide 26: Calculating Probabilistic Activity Times
Three Time Estimates
  pessimistic (a)
  most likely (m)
  optimistic (b)

## Slide 27: Figure 5-13 The Statistical Distribution of all Possible Times for an Activity

## Slide 28: Activity Expected Time and Variance

## Slide 29: 95 Percent Level
Task will be a or lower 5 percent of the time
Task will be b or greater 5 percent of the time

## Slide 30: 90 Percent Level
Task will be a or lower 10 percent of the time
Task will be b or greater 10 percent of the time

## Slide 31: 95 Percent Level (Alternative Interpretation)
Task will be between a and b 95 percent of the time

## Slide 32: 90 Percent Level (Alternative Interpretation)
Task will be between a and b 90 percent of the time

## Slide 33: Figure 5-14 An AON Network

## Slide 34: Figure 5-15 An MSP Version of a Sample Problem Network

## Slide 35: Figure 5-16 A Pert/CPM Network for the Day Care Project

## Slide 36: Figure 5-17 An MSP Calendar for the Day Care Project, 4/16/00 to 5/27/00

## Slide 37: The Probability of Completing the Project on Time
=NORMDIST(D,,,TRUE)

## Slide 38: Figure 5-18 The Statistical Distribution of Completion Times of the Path a-b-d-g-h

## Slide 39: Selecting Risk and Finding D
NORMINV(probability,,,TRUE)

## Slide 40: SIMULATION

## Slide 41: Traditional Statistics Versus Simulation
Similarities
  must enumerate alternate paths
Differences
  simulation does not require assumption of path independence

## Slide 42: Figure 5-20 The Distribution of Project Completion Times

## Slide 43: THE GANNT CHART

## Slide 44: Figure 5-21 A Gantt Chart of a Sample Project

## Slide 45: Figure 5-22 A Gantt Chart of Sample Project Showing Critical Path, Path Connections, Slack, EST, LST, EFT, and LFT

## Slide 46: Figure 5-23 A Gantt Chart of a Day Care Project Showing Expected Durations, Critical Path, Milestone, and Resource Requirements

## Slide 47: Figure 5-24 A Progress Report on a Day Care Project Showing Actual Progress Versus Baseline

## Slide 48: EXTENSIONS TO PERT/CPM

## Slide 49: Precedence Diagramming
Finish-to-start linkage
Start-to-start linkage
Finish-to-finish linkage
Start-to-finish linkage

## Slide 50: Figure 5-25 Precedence Diagramming Conventions

## Slide 51: Other Methods
Graphical Evaluation and Review Technique (GERT)
  combines flowgraphs, probabilistic networks, and decision trees
  allows loops back to earlier events and probabilistic branching

## Slide 52: Copyright
Copyright John Wiley & Sons, Inc. All rights reserved. Reproduction or translation of this work beyond that named in Section 117 of the United States Copyright Act without the express written consent of the copyright owner is unlawful. Requests for further information should be addressed to the Permissions Department, John Wiley & Sons, Inc. Adopters of the textbook are granted permission to make back-up copies for their own use only, to make copies for distribution to students of the course the textbook is used in, and to modify this material to best suit their instructional needs. Under no circumstances can copies be made for resale. The Publisher assumes no responsibility for errors, omissions, or damages, caused by the use of these programs or from the use of the information contained herein.