## Slide 1: Project Management in Practice
Prepared by
Scott M. Shafer
Wake Forest University
Mantel, Meredith, Shafer, and Sutton
John Wiley and Sons, Inc.

## Slide 2: Chapter 6
Allocating Resources to the Project

## Slide 3: Introduction
Projects Compete With One Another for Resources
  resources that are not consumed
  resources that are consumed
Goal of Resource Allocation is to Optimize Use of Limited Supply
Requires making trade-offs
  time constrained
  resource constrained

## Slide 4: EXPEDITING A PROJECT

## Slide 5: The Critical Path Method
Normal Duration Estimates
Normal Costs
Crash Duration Estimates
Crash Costs
Crash Cost Per Day

## Slide 6: Figure 6-1(a) Gantt Chart Crash Problem -- 21-Day Project

## Slide 7: Figure 6-1(b) AON Network for Sample Crash Problem -- 21-Day Project

## Slide 8: Figure 6-2 Gantt Chart for 20-Day Solution to Crash Problem

## Slide 9: Figure 6-3 Gantt Chart for 19-Day Solution to Crash Problem

## Slide 10: Figure 6-4 Gantt Chart for 18-Day Solution to Crash Problem

## Slide 11: Figure 6-5 Gantt Chart for 16-Day Solution to Crash Problem

## Slide 12: Figure 6-6 Project Cost Versus Project Duration for Sample Crash Problem

## Slide 13: Probabilistic Activity Durations
Three time estimates made for both normal resource loading and crash resource loading
Variance of normal activity may be different than variance of crash time

## Slide 14: Using Excel’s Solver to Crash a Project
Target Cell
  minimize crashing costs
By Changing Cells
  amount to crash activities
  time events occur
Constraints
  amount each activity can be crashed
  precedence relationships
  complete project by specified time
  nonnegativity

## Slide 15: Figure 6-7 AOA Network of Sample “Crash” Problem

## Slide 16: Figure 6-9 Cost/Duration Graph for Sample Crashing Project

## Slide 17: Fast-Tracking a Project
Used Primarily in Construction Industry
Building phase started before design and planning phases completed
Particularly appropriate when large proportion of work is routine

## Slide 18: RESOURCE LOADING

## Slide 19: Resource Loading
Amount of specific resources that are scheduled for use on specific activities or projects at specific times.
Usually a list or table.

## Slide 20: Figure 6-10 Action Plan and Gantt Chart for Production of a Videotape

## Slide 21: The Charismatic VP
Subordinates have hard time saying no to well liked boss.
Leads to overcommitted subordinates.
Problem further compounded because more experienced workers tend to be most over worked.
One solution is to set specific limits on amount of overscheduling permitted.

## Slide 22: RESOURCE LEVELING

## Slide 23: Figure 6-11 Gantt Chart for Videotape Project, Adjusted for Client Availability

## Slide 24: Figure 6-12 Resource Overallocation Report for Scriptwriter Showing all Activities

## Slide 25: Figure 6-13 Graphic Resource Overallocation Report for Scriptwriter

## Slide 26: Figure 6-14 Resource Leveled Report for Scriptwriter Showing all Activities

## Slide 27: Figure 6-15 Graphic Resource Leveled Report for Scriptwriter

## Slide 28: Figure 6-16 Daily Resource Loading Chart for Videotape Project, Scriptwriter Leveled

## Slide 29: Figure 6-17 Final Videotape Project Gantt Chart Schedule, With Two Scriptwriters and Producer Leveled

## Slide 30: Resource Loading/Leveling and Uncertainty
28,282 Hours Needed
Group Capacity
  21 (people)  40 (hrs/wk)  34 wk = 28,560 labor hrs
Correction for Holidays
  21  3 (days)  8 (hours) = 504 labor hrs
Vacations
  11  2 (weeks)  40 = 880 labor hrs

## Slide 31: Resource Loading/Leveling and Uncertainty continued
Hours Available
  28,560 - 504 - 880 = 27,176
  about 1100 less than needed
  28,282/27176 = 1.04
What about
  Workers getting sick?
  Task not ready when worker is ready?
  Change orders?

## Slide 32: Figure 6-18 Thirty-Four-Week Resource Loading Chart for a Software Engineering Group

## Slide 33: ALLOCATING SCARCE RESOURCES TO PROJECTS

## Slide 34: Use of Software
Begin with Pert/CPM Schedule
Activities examined period by period and resource by resource
In cases where demand for resource exceeds supply, tasks considered one by one and resources assigned to these tasks based on priority rules

## Slide 35: Some Comments about Constrained Resources
Scarcity of resources rarely applies to resources in general
“Walts”

## Slide 36: Some Priority Rules
As soon as possible
As late as possible
Shortest task duration first
Minimum slack first
Most critical followers
Most successor
Most resources first

## Slide 37: Choosing a Priority Rule
Schedule Slippage
  amount project or set of projects delayed
Resource Utilization
  extent that resources are over or underworked
In-Process Inventory
  amount of unfinished work in the system

## Slide 38: ALLOCATING SCARCE RESOURCES TO SEVERAL PROJECTS

## Slide 39: Pseudoactivities
Used to link several project together
Have duration but do not require any resources
This approach allows a set of projects to be dealt with as though it were a single project
  use of MSP’s resource loading and leveling charts and tables

## Slide 40: Figure 6-19 Multiple Projects Connected with Pseudoactivities Shown on a Time Line

## Slide 41: Resource Allocation and the Project Life Cycle
Figure 6-20 Project or task life cycles

## Slide 42: GOLDRATT’S CRITICAL CHAIN

## Slide 43: Introduction
Similar issues that trouble people about working on projects regardless of type of project
  unrealistic due dates
  too many changes
  resources and data not available
  unrealistic budget
These issues/problems related to need to make trade-offs
To what extent are these problems caused by human decisions and practices?

## Slide 44: Figure 6-21 Three Project Scenarios

## Slide 45: Table 6-6 Project Completion Time Statistics Based on Simulating Three Projects 200 Times

## Slide 46: Observations
Average Completion Times
Implications of Assuming Known Activity Times
Shape of the Distribution
Worker Time Estimates
Impact of Inflated Time Estimates
Student Syndrome

## Slide 47: Multitasking
Figure 6-22 Two Small Projects

## Slide 48: Figure 6-23 Alternative Gantt Charts for Projects A and B

## Slide 49: Common Chain of Events
Underestimate time needed to complete project
  assumption of known activity times and independent paths
Project team members inflate time estimates
Work fills available time
  student syndrome
  early completions not reported

## Slide 50: Common Chain of Events continued
Safety time misused
Misused safety time results in missed deadlines
Hidden safety time complicates task of prioritizing project activities
Lack of clear priorities results in poor multitasking

## Slide 51: Common Chain of Events concluded
Poor multitasking increases task durations
Uneven demand on resources also results due to poor multitasking
More projects undertaken to ensure all resources fully utilized
More projects further increases poor multitasking

## Slide 52: Reversing the Cycle
Reduce number of projects assigned to each individual
Schedule start of new projects based on availability of bottleneck resources
Reduce amount of safety time added to individual tasks and then add some fraction back as project buffer
  activity durations set so that there is a high probability the task will not be finished on time

## Slide 53: The Critical Chain
Longest chain of consecutively dependent events
  considers both precedence relationships and resource dependencies
Project Buffer
Feeding Buffer

## Slide 54: Figure 6-24 Sample Network Diagram

## Slide 55: Figure 6-25 Project and Feeder Buffers

## Slide 56: Copyright
Copyright John Wiley & Sons, Inc. All rights reserved. Reproduction or translation of this work beyond that named in Section 117 of the United States Copyright Act without the express written consent of the copyright owner is unlawful. Requests for further information should be addressed to the Permissions Department, John Wiley & Sons, Inc. Adopters of the textbook are granted permission to make back-up copies for their own use only, to make copies for distribution to students of the course the textbook is used in, and to modify this material to best suit their instructional needs. Under no circumstances can copies be made for resale. The Publisher assumes no responsibility for errors, omissions, or damages, caused by the use of these programs or from the use of the information contained herein.