## Slide 1: Project Management in Practice
Prepared by
Scott M. Shafer
Wake Forest University
Mantel, Meredith, Shafer, and Sutton
John Wiley and Sons, Inc.

## Slide 2: Chapter 7
Monitoring and Controlling the Project

## Slide 3: Introduction
Monitoring and Control are opposite sides of selection and planning
  bases for selection dictate what to monitor
  plans identify elements to control
Monitoring is collection, recording, and reporting of information
Control uses monitored information to align actual performance with the plan

## Slide 4: THE PLAN-MONITOR-CONTROL CYCLE

## Slide 5: Plan-Monitor-Control Cycle
Closed loop process
Planning-monitoring-controlling effort often minimized to spend time on “the real work”

## Slide 6: Figure 7-1 Project Authorization and Expenditure Control System Information Flow

## Slide 7: Designing the Monitoring System
Identify special characteristics of performance, cost, and time that need to be controlled
  performance characteristics should be set for each level of detail in the project
Real-time data should be collected and compared against plans
  mechanisms to collect this data must be designed
Avoid tendency to focus on easily collected data

## Slide 8: DATA COLLECTION AND REPORTING

## Slide 9: Formats of Data
Frequency Counts
Raw Numbers
Subjective Numeric Ratings
Indicators and Surrogates
Verbal Characterizations

## Slide 10: Data Analysis
Aggregation Techniques
Fitting Statistical Distributions
Curve Fitting
Quality Management Techniques

## Slide 11: Figure 7-2 Number of Bugs per Unit of Test Time

## Slide 12: Figure 7-3 Percent of Specified Performance Met During Successive Repeated Trials

## Slide 13: Figure 7-4 Ratio of Actual Material Cost to Estimated Material Cost

## Slide 14: Reporting
Reports
  Project Status Reports
  Time/Cost Reports
  Variance Reports
Not all stakeholders need to receive same information
Avoid periodic reports
Impact of Electronic Media
Relationship between project’s information system and overall organization’s information system

## Slide 15: Report Types
Routine
Exception
Special Analysis

## Slide 16: Meeting Guidelines
Meetings should be help primarily for group decision making
  avoid weekly progress report meetings
Distribute written agenda in advance of meeting

## Slide 17: Meeting Guidelines continued
Ensure everyone is properly prepared for meeting
Chair of meeting should take minutes
  avoid attributing remarks to individuals in the minutes
Avoid excessive formality
If meeting is held to address specific crisis, restrict meeting to this issue alone

## Slide 18: Virtual Reports, Meetings, and Project Management
Use of the Internet
Use of Software Programs
Virtual Project Teams

## Slide 19: EARNED VALUE

## Slide 20: Earned Value
Percent of task’s budget actually spent not good indicator of percent completion

## Slide 21: Conventions Used to Estimate Progress on Tasks
50-50
  50% complete when task started and other 50% added when task finished
100%
  100% complete when finished and zero percent before that
Ratio of Cost Expended to Cost Budgeted

## Slide 22: Variances
Cost/Spending Variance
  BCWP - ACWP
Schedule Variance
  BCWP - BCWS
CPI
  BCWP/ACWP
SPI
  BCWP/BCWS

## Slide 23: Figure 7-5 Earned Value Chart

## Slide 24: Figure 7-6(a) Positive Schedule Variance, Negative Spending Variance

## Slide 25: Figure 7-6(b) Negative Schedule Variance, Negative Spending Variance

## Slide 26: Figure 7-6(c) Negative Schedule Variance, Positive Spending Variance

## Slide 27: Additional Items of Interest
Estimated (Remaining Cost) to Completion
  ETC = (BAC - BCWP)/CPI
(Total Cost) Estimated at Completion
  EAC = ETC + ACWP

## Slide 28: PROJECT CONTROL

## Slide 29: Background
Acts which seek to reduce differences between plan and actuality
Difficult Task
  human behavior involved
  problems rarely clear cut

## Slide 30: Purposed of Control
Stewardship of Organizational Assets
  physical asset control
  human resources
  financial control
Regulation of Results Through the Alteration of Activities

## Slide 31: DESIGNING THE CONTROL SYSTEM

## Slide 32: Background
Purpose is to correct errors, not punish the guilty
Investments in control subject to diminishing returns
Must consider impact on creativity and innovation
Be careful not emphasize short-run results at the expense of long-run objectives
Dangers of across the board cuts

## Slide 33: Primary Mechanisms by Which PM Exerts Control
Process Reviews
Personnel Assignments
Resource Allocations

## Slide 34: Components of a Control System
Sensor
Standard
Comparator
Decision Maker
Effector

## Slide 35: Types of Control Systems
Go/No-Go Controls
  predetermined standard must be met for permission to be granted to continue
Post-Control
  done after project completed
  purpose is to allow future projects to learn from past project experience

## Slide 36: Figure 7-7 Sample Project Milestone Status Report

## Slide 37: Tools for Control
Variance Analysis
Trend Projections
Earned Value Analysis
Critical Ratio

## Slide 38: Figure 7-8 Trend Projection

## Slide 39: Figure 7-9 Critical Ratios with Control Limits

## Slide 40: Figure 7-10 Cost Control Chart

## Slide 41: SCOPE CREEP AND CHANGE CONTROL

## Slide 42: Scope Creep
Coping with changes frequently cited by PMs as the single most important problem
Common Reasons for Change Requests
  Client
  Availability of new technologies and materials

## Slide 43: Purpose of Change Control System
Review all requested changes
Identify impact of change
Evaluate advantages and disadvantages of requested change
Install process so that individual with authority may accept or reject changes

## Slide 44: Purpose of Change Control System continued
Communicate change to concerned parties
Ensure changes implemented properly
Prepare reports that summarize changes made to date and their impact

## Slide 45: Rules for Controlling Scope Creep
Include in contract change control system
Require all changes be introduced by a change order
Require approval in writing by the client’s agent and senior management
Consult with PM prior to preparation of change order
Amend master plan to reflect changes

## Slide 46: Copyright
Copyright John Wiley & Sons, Inc. All rights reserved. Reproduction or translation of this work beyond that named in Section 117 of the United States Copyright Act without the express written consent of the copyright owner is unlawful. Requests for further information should be addressed to the Permissions Department, John Wiley & Sons, Inc. Adopters of the textbook are granted permission to make back-up copies for their own use only, to make copies for distribution to students of the course the textbook is used in, and to modify this material to best suit their instructional needs. Under no circumstances can copies be made for resale. The Publisher assumes no responsibility for errors, omissions, or damages, caused by the use of these programs or from the use of the information contained herein.