Feasibility Study

Feasibility Study (Business Vision) –

Incidents Tracking and Help Desk System (IT&HELP)

Lucio Gayosso

University of Phoenix

CMGT 555

Ed Odjaghian

10/17/2005

Contents

Contents	2

Introduction	3

Purpose	4

Benefits	4

Tangible	4

Intangible	5

Solutions	5

Custom	5

Purchased solutions	6

Outsourcing	6

Hybrid	7

Costs	7

Custom Development.	7

Purchased Solutions	8

Schedule	9

Phases and timelines..	9

References	11

- Introduction

- This document evaluates the feasibility for building an Incidents Tracking and Help Desk System (IT&HELP) for Company X (CX), a Judicial Solutions software development firm.

- CX counts with two main departments: Development and Support, which together cover the entire systems development life cycle and use a variety of tools to communicate with customers and perform systems maintenance and support, and track enhancements requests. The tools currently used are off-the shelf packages from multiple vendors which in certain instances do not comply with the standard processes the organization possesses.

- The inherent complexity of the muti-tool configuration confuses employees in the two main departments as to what is the standard procedure to achieve day-to-day tasks and this has, in some instances, generated conflicts. Issues where customer is involved can exacerbate such conflicts.

- Customers frequently complain about the lack of access to a system that allows them to enter and track issues.

- IT&HELP is an in-house project carried out by CX’ development group which should eliminate 3rd party vendors’ solutions by providing a custom system that fully complies with current procedures.

- By providing all development resources, CX would also be enabled to perform any future IT&HELP modification or enhancement to comply with new projects’ requirements or tailor to account for unexpected challenges (such as RIF, new reporting regulations, etc).

- Purpose

IT&HELP has the following primary goals (by ascending priority):

- Simplification of bugs and incidents’ reporting process

- Enhanced Development and Support groups collaboration

- Enhanced interdepartmental communication

- Reduction in the number of tools CX needs for day-to-day operations

- Accurate tracking of tickets’ lifecycle

- Instant communication of ticket status changes

- Expedite documentation of incidents’ resolution

- Generation of a Knowledge Base (KB) based on Incidents resolution

- Automation of solutions, fixes, and patch deployment

- Benefits

- Tangible

  - Overall operation costs reduction. IT&HELP would either eliminate or significantly decrease the need for 3rd party solutions (no more upgrades or maintenance fees). Total savings could be up to $10,000/year for licensing and maintenance agreements reduction and/or elimination.

  - Decreased bugs fix and incident resolution time due to more efficient reporting, resource allocation and collaboration, and expedite customer communication. This could represent up to 33% improvement on daily operations which might  represent up to $329,472/year (33% of 8 hr/days @ average $40 hr for 240 day/years for 13 employees)

  - Reduced learning curve for new staff as just one tool would be used to support daily core activities

- Intangible

  - Formalization and standardization of internal procedures which would expedite customer’s attention and provide an overall professional service

  - Decrease of internal conflicts (intra and interdepartmental) due to misinterpretation of standard procedures

  - CX’ empowerment to retain autonomy of its IT operations. IT&HELP can provide an in-house solution which could be tailored to account for future needs.

- Solutions

- Custom

  - CX counts with a qualified development group with strong and diverse skill sets featuring Client/Server technologies, .NET development, mission-critical OO methodologies, among others

  - CX personnel have carried various systems’ entire life cycle development

  - Majority of the staff has several years of experience in the judicial area scoped by CX project.

  - Software Development tools and hardware are already available

- Purchased solutions

  - Current approach

  - Expensive as licensing, maintenance, and support fees have been increasing steadily in the last years.

  - Multiple applications are required on a daily basis: TeamTrack (incident and bug tracking application), SharePoint (a collaboration portal for intracorporate communications), Outlook Express (collaboration tool), AOL and Microsoft’s Instant Messaging applications, among others

- Outsourcing

  - Unfeasible because:

    - Organization size.

      - CX is a small firm (less than 25 employees) and cannot afford outsourcing and maintain current staff’s training, salaries, and benefits (Development group currently undergoing training for technologies that will be used in new projects)

      - Number of employees in Management groups (top and middle levels) is insufficient to supervise internal and outsourced operations

    - No previous outsource experience.

- Hybrid

  - Unfeasible because:

    - Used solutions are not Open Source projects and do not provide source and integration facilities

    - Staff inexperienced in 3rd party systems architecture and design

    - Very expensive 3rd party solutions’ customization

- Costs

- Custom Development.

  - Training (formal and informal): $0.00 (staff already has the required skills to build the system)

  - Development tools licenses and fees: $0.00 (CX already counts with development tools that can be used on the project)

  - Hardware to develop and implement system: $0.00 (CX has recently upgraded servers which can allocate resources to support development and host final implementation).

  - Development: Average $30-50/man-hr (this cost represents the core of the development of IT&HELP)

  - Documentation: $30-40/man-hr (this cost is inexpensive as CX counts with a technical writer)

  - Training: Close to $0.00 (this cost would be minimal as learning curve would not be steep considering the staff to be trained participated in the development efforts)

  - Total Ownership Cost (TCO): Considering 3.5 months (8 hr/day participation of 5 members): 960 hrs X 5 members = 2800 hrs @ Avg $40/man-hr = $ 112,000.

  - ROI: Shelly, G. B., Cashman, T. J., & Rosenblatt, H. J. (2004) explain this represents a percentage rate that measures profitability by contrasting the total net benefits to the total costs of a project (p. 548). IT&HELP can provide a ROI of = (Total Benefits – Total Costs)/Total Costs = ($339,472 - $112,000)/ $112,000 = 2.031 = 203.1 %.

- Purchased Solutions

  - Licenses and fees: $10,000 annual licensing, maintenance and upgrade costs.

  - Training (formal and informal): High turnover rate has resulted in average 8 week-training for new employees to become proficient with daily tasks.

  - Documentation: Lack of formalization in incidents and bugs resolutions amounts for up to 50% of technical writer’s work time,

  - Indirect costs:

    - Delayed response in Incidents allocation and resolutions’ tracking. CX counts with 13 employees in Support and Development groups. The cost of this time delay could surmount to be $329,472/year (33% of 8 hr/day @ average $40 hr for 240 day/years)

    - User’s perception of delayed response

    - Internal conflicts due to processes misunderstandings. This might be cause of increase in employee’s turnover rate.

  - Total Ownership Cost (TCO): $339.472/year

- Schedule

- The proposed solution accounts for an SDLC approach to the system construction as described by UoP (2005).

- 8 hr days/20 day months/5 employees considered (three developers with strong analysis skills, one systems analyst, and one support specialist)

- Phases and timelines:

  - Project Initiation (4 days). Main activities:

    - Determination of scopes and objectives of IT&HELP

    - Feasibility Report

  - Analysis (10 days). Main activities:

    - Documentation of existing activities to be automated with IT&HELP

    - Interviews with end users and observation of their activities

    - Development of Systems Requirements Specification (SRS) applying Systems Requirements Engineering principles

  - Design (20 days). Main activities:

    - Modeling stages (Process, Network, and Data Modeling)

    - Writing of IT&HELP System Specifications

  - Development (30 days). Main activities

    - Coding of IT&HELP using CX existing development tools and OO methodologies

    - Testing (parallel of internal and end-user testing)

    - Documentation (system and end user)

  - Implementation (5 days). Main activities:

    - Installation

    - Training

  - Maintenance (0 days). Outside of scope. Second phase of IT&HELP will be considered for this task.

  - TOTAL PROJECT TIMELINE: 70 days (3.5 CALENDAR MONTHS).

References

Shelly, G. B., Cashman, T. J., & Rosenblatt, H. J. (2004). Systems Analysis and Design (5th Ed). Course Technology, 640.

UoP (2005). CMGT/555 Course Notes. University of Phoenix.